## Instructions (EXTERNAL)
London Borough of Richmond upon Thames LFRMS Action Plan
The Action Plan supports the delivery of the London Borough of Richmond Upon Thames LFRMS.
It is intended to be used by the Richmond Lead Local Flood Authority. (FOR EXTERNAL USE)
Version: 2.0
Last Updated: May 2022
LFRMS Strategic Objectives
A | To improve our knowledge and understanding of the risk of flooding and the interactions between different sources of flooding across the London Borough of Richmond upon Thames.
B | To encourage appropriately mitigated development across the London Borough of Richmond upon Thames by promoting sustainable multi-beneficial solutions to contribute to wider social, economic, and environmental outcomes.
C | To seek and identify funding and resources available for a targeted approach to flood risk management.
D | To proactively manage sources of local flooding to homes, critical infrastructure, and transport networks by establishing and maintaining partnerships with key organisations, including the Environment Agency and Thames Water.
E | To work with Risk Management Authorities to raise awareness of flood risk with communities, residents and businesses, and how they can take action to protect themselves and their property by contributing to the management and reduction of flood risk.
F | To use knowledge of flood risk and climate change projections to inform and adapt the emergency response to flooding within the London Borough of Richmond upon Thames.
Key
* | Action IDs with an asterisk symbol are actions which are in both the Richmond and Wandsworth LFRMS Action Plans. Funding, Delivery, Programme and Monitoring may differ between each borough.
Table headings/sections
Actions |  | Information relating to each action and associated objective.
Funding |  | Estimated cost for action delivery and potential funding sources required.
Delivery |  | The proposed RMAs involved in the delivery of each action.
Programme |  | Proposed timescales for the action and each action's current status of progress.
Monitoring |  | Information on the monitoring procedure and regularity with any additional comments on progress of the LFRMS action.
Items
Strategic Objective |  |  | Strategic objective letter as defined in the LFRMS document.
Action ID |  |  | The individual action ID value.
Action Details |  |  | Action description.
Lead Risk Management Authority |  |  | The organisation which will lead in the delivery of the action.
Partner Authorities / Departments |  |  | The organisations which will support the delivery of the action.
Timescale from 2022 |  |  | The approximate time period for completing the action from the publication of the LFRMS, or if the action is an ongoing deliverable.
Current Status |  |  | The current status of the actions progress in being completed.
Links to Legislation / Policy |  |  | Hyperlinks to legislation that links to the delivery of this action. FWMA = Flood and Water Management Act 2010 NFCERMS = National Flood and Coastal Erosion Risk Management Strategy CCSS = Richmond Climate Change and Sustainability Strategy (CCSS) Action Plan WAN = Thames River Basin District - Flood Risk Management Plan (FRMP) - Wandsworth SWMP = Surface Water Management Plan (SWMP) Action Plan
Dropdowns
Timescale from 2022 |  |  | Current Status
Short-term = 0-2 years |  |  | Red | Action is not currently in progress
Medium-term = 2-4 years |  |  | Amber | Action is in progress
Long-term = 4-6+ years |  |  | Green | Action completed
On-going = Continual action

## LFRMS Action Plan EXTERNAL
London Borough of Richmond upon Thames LFRMS Action Plan
The Action Plan supports the delivery of the London Borough of Richmond upon Thames LFRMS.
It is intended to be used by the Richmond Lead Local Flood Authority (LLFA). (FOR EXTERNAL USE)
Refer to the 'Instructions' Tab for a description of the contents of the Action Plan.
Version: 2.0
Last Updated: May 2022
Actions |  |  | Delivery |  | Programme |  | Links to Legislation / Policy
Strategic Objective | Action ID | Action Details | Lead Risk Management Authority | Partner Authorities / Departments | Timescale from 2022 | Current Status
A | A1* | Identify assets that are considered to have a significant effect on local flood risk and perform an asset inspection program using outputs from the Surface Water Managment Plan to identify and prioritise assets that are considered to be of higher risk, particularly in Hotspot areas. | Richmond LLFA | Environment Agency Thames Water Transport for London | Short-term | Amber | FWMA (2010)
LBRuT_02_08_19 LBRuT_02_09_20
SWMP Action 2 SWMP Action 10
CCSS Action 131 CCSS Action 136
| A2* | Review lessons learnt from Summer 2021 surface water flooding incidents. | Richmond LLFA | Richmond Emergency Planning Environment Agency Thames Water South London LLFAs | Short-term | Amber | LBRuT_02_06_15
CCSS Action 136
| A3* | Work with partner Risk Management Authorities such as the Environment Agency and Thames Water to identify areas where flood risk through partnership planning and workshops (e.g. surface water and sewer or river, could combine to exacerbate flood risk to inform resilient drainage and sewerage management plans). | Richmond LLFA | Richmond Emergency Planning Richmond Highways Thames Water Environment Agency Transport for London | Short-term | Red | NFCERMS - Measure 2.7.1
LBRuT_01_04_08
| A4* | Review Surface Water Management Plan outcomes and recommendations in line with updated and emerging datasets and historical incidents of local flood risk. | Richmond LLFA |  | Short-term | Red | LBRuT_02_05_10
CCSS Action 133
SWMP Action 2
| A5* | Review and update Flood Incident Database through monitoring and adding tasks. | Richmond LLFA |  | Short-term | Red | LBRuT_02_06_ 15
CCSS Action 133 CCSS Action 135 CCSS Action 136
| A6 | Review and make relevant Council teams aware of the borough's published Local Flood Risk Management Strategy update. Incorporate links / risks into carbon literacy training. | Richmond LLFA | Assistant Chief Executive (Climate Policy) | Short-term | Red | FWMA (2010)
LBRuT_01_01_02
CCSS Action 21
| A7 | Evaluate and upload asset data to Council's GIS systems and provide to London Drainage Engineers Group (LoDEG) to support their asset management database, feed into integration with other datasets to support councils climate risk/vulnerability mapping. | Richmond LLFA | Assistant Chief Executive (Climate Policy / Insight and Analytics) | Short-term | Amber | LBRuT_02_08_19
CCSS Action 133 CCSS Action 135
| A8 | Regularly review the Strategic Flood Risk Assessment and ensure mapping is the most up to date versions to provide developers with the most up to date information. | Richmond Local Planning Authority | Richmond LLFA Environment Agency | On-going | Amber | National Planning Policy Framework (2021, revised)
Strategic Flood Risk Assessment (2016)
LBRuT_04_14_34
SWMP Action 12
| A9 | Assess planned flood risk management schemes against the Water Framework Directive. | Richmond LLFA |  | Short-term | Red | LBRuT_05_17_43
B | B1* | Ensure appropriate applications for new major developments, particularly in Surface Water Management Plan Hotspots, contribute to measures to reduce surface water flood risk in the Catchment through the incorporation of rainwater harvesting, green / blue infrastructure and SuDS. | Richmond LLFA | Richmond Local Planning Authority | Medium-term | Amber | Local Plan Policy 12 - Green Infrastructure Local Plan Policy 17 - Green Roofs and Walls Local Plan Policy 21 - Flood risk and Sustainable Drainage
LBRuT_04_14_37 LBRuT_04_14_38 LBRuT_04_14_35
SWMP Action 11 SWMP Action 13
CCSS Action 45 CCSS Action 127 CCSS Action 140
| B2* | Support the development of planning skills and capabilities needed to ensure new developments and spatial plans are resilient to flooding and coastal change. | Richmond LLFA |  | Medium-term | Red | NFCERMS - Measure 2.1.4
LBRuT_04_14_36 LBRuT_04_14_37
| B3* | Contribute to improving the natural, built, and historic environment by investing in appropriate projects that manage flood and coastal risk and work with local environmental groups to utilise best practices. | Richmond LLFA | Richmond Planning Habitats and Heritage (Formally Southwest London Environment Network) FORCE | Medium-term | Red | NFCERMS - Measure 1.4.3
LBRuT_05_17_43 LBRuT_05_17_44
SWMP Action 7
| B4* | Identify opportunities for tackling environmental and social issues together by assessing proposed schemes for social impacts and improve awareness in the community to tackle flood risk problems and social issues simultaneously. | Richmond LLFA |  | Short-term | Red | LBRuT_05_18_45 LBRuT_05_18_46
SWMP Action 7
CCSS Action 128 CCSS Action 129 CCSS Action 130
| B5* | Work with developers and planners to maximise opportunities for flood and coastal resilience as part of contributing to environmental net gain for development proposals, including requirements around biodiversity net gain. | Richmond LLFA | Richmond Environmental Services Biodiversity Team Natural England | Long-term | Red | NFCERMS - Measure 2.2.2
Biodiversity Action Plan (2019)
SWMP Action 7 SWMP Action 11
CCSS Action 45 CCSS Action 107 CCSS Action 108
| B6* | Seek to reduce carbon emissions associated with flood risk schemes with the aim of making them carbon neutral, considering and reducing the embodied carbon of infrastructure materials. | Richmond LLFA |  | Long-term | Red | Local Plan (2018)
Mayor of London’s Environment Strategy (2018)
The London Plan (2021)
SWMP Action 17
| B7 | Work with Risk Management Authorities, catchment partnerships, land managers and communities to mainstream and identify opportunities to incorporate Natural Flood Management in the borough. | Richmond LLFA |  | Short-term | Red | NFCERMS - Measure 1.4.2
LBRuT_05_17_44
SWMP Action 18
| B8 | Update planning advice for SuDS and flood risk in line with the non-statutory technical standards for Sustainable Drainage Systems and produce guidance on Sustainable Drainage Systems for use by planning applicants and council officers. | Richmond LLFA | Richmond Planning | Short-term | Red | National Planning Policy Framework (2021, revised)
The SuDS Manual (C753F)
LBRuT_04_14_37
SWMP Action 16
CCSS Action 142
| B9 | Progress proposed flood risk schemes at Strawberry Vale, Marlow Crescent and publish successes on the Council’s website. Cost estimate for website updates only. | Richmond LLFA | Richmond Planning | Medium-term | Amber
| B10 | Use schemes to reconnect people to the natural environment helping to improve mental and physical wellbeing. | Richmond LLFA | Richmond Community Engagement Team Richmond communications Social care services Healthcare services Mental health charities | Short-term | Amber | Local Plan Policy 12 – Green Infrastructure Local Plan Policy 18 – River corridors
C | C1* | Work with a range of partners to trial different finance options to help close funding gaps for flood risk management projects, prioritising locations for shovel-ready projects for e.g. SuDS. | Richmond LLFA | Flood Re ADEPT Rivers Trust | Long-term | Red | NFCERMS - Measure B1
LBRuT_02_07_16 LBRuT_05_19_48
SWMP Action 6
CCSS Action 144
| C2* | Monitor and review funding opportunities, both internal and external, for local flood risk management activities. | Richmond LLFA |  | On-going | Red | LBRuT_05_19_48
SWMP Action 3 SWMP Action 5
CCSS Action 135 CCSS Action 137
| C3* | Produce and maintain a list of ongoing / potential flood risk management schemes on an annual basis and share with Risk Management Authorities, residents and businesses to identify partnership funding provisions / requirements. | Richmond LLFA | Environment Agency Thames Water Transport for London Neighbouring LLFAs | On-going | Red | LBRuT_02_07_16
SWMP Action 3 SWMP Action 6
CCSS Action 134 CCSS Action 135 CCSS Action 139
| C4 | Undertake full lifecycle cost benefit analysis for flood risk management schemes. Cost per scheme. | Richmond LLFA |  | Short-term | Red | LBRuT_05_19_47
SWMP Action 3
CCSS Action 134
| C5 | Identify sources of funding and assistance for retrofitting roofs on residential and commercial buildings with green or blue roofs. | Richmond LLFA |  | Short-term | Red | SWMP Action 13
CCSS Action 140
D | D1* | Keep up to date with current Environment Agency, Met Office, and Flood Forecasting Centre on surface water flood forecasting initiatives, and any updates to flood warning systems. | Richmond LLFA | Environment Agency | On-going | Red | LBRuT_03_12_30 LBRuT_03_12_31
| D2* | Continue to conduct maintenance of the drainage system such as ensuring gullies and drains are regularly maintained to allow the drainage network to operate at capacity particularly in Surface Water Management Plan Hotspots. | Richmond Highways | Richmond LLFA Thames Water Transport for London Highways England | On-going | Amber | FWMA (2010)
LBRuT_04_15_39
SWMP Action 9
| D3 | Continue to hold quarterly Flood Group meetings and distribute the minutes and assigned actions to all relevant Risk Management Authorities and absentees as relevant. | Richmond LLFA | South West London Flood Group Environment Agency | On-going | Amber | LBRuT_01_02_04 LBRuT_01_03_05
SWMP Action 1
CCSS Action 143
| D4 | Maintain regular contact with managers and/or officers dealing with flood risk matters in neighbouring boroughs to ensure awareness of cross-boundary projects or initiatives. | Richmond LLFA |  | On-going | Amber | LBRuT_01_03_06
SWMP Action 1
| D5 | Review and update Risk Management Authorities and stakeholder contacts including the Environment Agency, Transport for London, UK Power Networks, Network Rail, Greater London Archaeological Advisory Services, English Heritage, and local environmental groups such as Habitats and Heritage and Friends of the River Crane Environment etc. | Richmond LLFA | Environment Agency Transport for London UK Power Networks Network Rail | Long-term | Amber | LBRuT_01_01_01
| D6 | Provide training for other Council officers to increase the potential for partnership working through improved education about SuDS and to improve public communication practices. | Richmond LLFA | Internal council departments (as relevant) | Short-term | Red | NFCERMS - Measure 3.1.2
LBRuT_03_10_21
SWMP Action 16
CCSS Action 142
E | E1* | Maintain online flood reporting tool, provide regular updates of any actions taken to the reporter, and encourage the public to report incidents using this web-based form. | Richmond LLFA |  | On-going | Red | LBRuT_02_06_13 LBRuT_02_06_14 LBRuT_02_06_15
| E2* | Contact relevant community representatives outlining Richmond's LLFA duties and responsibilities, and signpost current flood risk information available. Helping to improve the education within the local community on flood risks and support the uptake of Property Flood Resilience measures. | Richmond LLFA | Richmond Community Engagement Team Richmond Emergency Planning | Short-term | Red | LBRuT_03_10_21 LBRuT_03_10_22
SWMP Action 14
CCSS Action 133 CCSS Action 140
| E3* | Aid existing and the establishment of local flood groups in supporting people living in places at high risk of flooding in developing and testing local flood plans. | Richmond LLFA | Richmond Community Engagement Team Richmond Emergency Planning | Short-term | Red | NFCERMS - Measure 3.2.4
LBRuT_03_11_28
SWMP Action 14
| E4* | Reduce economic damage in the borough by investigating schemes which protect local businesses, whilst establishing and maintaining contacts with business groups holding briefings if appropriate to inform those in flood risk areas where to go for further information. | Richmond LLFA |  | Short-term | Red | LBRuT_03_11_28 LBRuT_05_19_49 LBRuT_02_06_12
CCSS Action 139 CCSS Action 140
| E5* | Review and consolidate Richmond Council's flood related webpages combining information into one easily accessible location on the website. Ensure this includes appropriate links to external websites for further guidance, including links to the Environment Agency's website for signing up to flood warnings and include these on any relevant communication material. | Richmond LLFA | Richmond Communications Environment Agency | Short-term | Red | LBRuT_02_05_11 LBRuT_03_10_24
| E6* | Develop an information package which can be distributed digitally via partner websites, used in presentations outlining the responsibilities of different Risk Management Authorities, how property owners can find out more information on flood risk and take action to protect their own property from flooding. | Richmond LLFA | Environment Agency Thames Water Richmond Communications Richmond Community Engagement Team | Short-term | Red | LBRuT_03_11_25
SWMP Action 14
CCSS Action 140
| E7 | Publicise on the Council's website the importance of ordinary watercourses and the responsibilities of private landowners with ordinary watercourses situated on their land. | Richmond LLFA |  | Short-term | Red | LBRuT_02_05_09 LBRuT_02_05_10
| E8 | Hold briefing sessions to inform councillors of the latest flood risk developments, as appropriate. | Richmond LLFA |  | Short-term | Amber | LBRuT_03_10_23
F | F1* | Use modelling from the Surface Water Management Plan and data on historical flooding incidents to prioritise flood risk response areas across Richmond. | Richmond LLFA | Richmond Emergency Planning Richmond Highways | Short-term | Red | Civil Contingencies Act (2004)
LBRuT_02_05_10
SWMP Action 2
CCSS Action 131 CCSS Action 139
| F2* | Attend Multi Agency Plan meetings to determine flood risk management and emergency response strategies including conducting regular formal review of the Multi Agency Flood Plan, the criteria that would instigate a review and the roles and responsibilities of Risk Management Authorities. | Richmond LLFA | Richmond Emergency Planning Environment Agency Thames Water Transport for London | On-going | Amber | Civil Contingencies Act (2004)
LBRuT_03_11_26
| F3* | Factor mental health impacts of flooding into long-term recovery planning by working with public health services and voluntary organisations. | Richmond LLFA | Richmond Emergency Planning Social care services Healthcare services Mental health charities | Short-term | Red | NFCERMS - Measure 3.3.3
SWMP Action 7
CCSS Action 128 CCSS Action 129 CCSS Action 130
| F4* | Review emerging climate change projections in line with existing and updated flood risk assessments. | Richmond LLFA |  | Long-term | Red | IPCC Climate Change Report (2021)
LBRuT_03_12_29
CCSS Action 131 CCSS Action 133
| F5* | Review flood investigation criteria for when flooding incidents will warrant an investigation and the protocol for delivering this. Publish these criteria on Council’s website. | Richmond LLFA | Environment Agency Richmond Communications | Short-term | Red | FWMA (2010)
| F6* | Record flooding incidents in a timely and consistent manner at the exact location of flooding. | Richmond LLFA | Thames Water | On-going | Amber | FWMA (2010)
LBRuT_02_06_13 LBRuT_02_06_14
SWMP Action 8